## Sheet1
Change Log: HL7_CDAR@_IG_PERSADVCAREPLAN_STU3 2023SEP
STU Update Confluence Site: https://confluence.hl7.org/pages/viewpage.action?pageId=175604961
Jira Ticket | Approve on Date | VS Update | Short Title | Notes |  | Vote Details | Summary of Changes
CDA-20440 | not persuasive 6/22/2023 | X | Updates to Race and Ethnicity Value Sets | no activity needed. |  | Lisa N/Gay D: 17-0-0 | Race and Ethnicity value sets didn't need to be updated.
CDA-20702 | 2023-06-22 | X | Change the Advance Directive Content Type to a Grouping Value Set | 6/26/2023 - made the VS Change, but template changes are now needed to update the conformance constraint to use the correct value set. Check Advance Directives Supplement as well as the PACP. |  | Lisa N/Gay D: 17-0-0 | Changed the Advance Directive Content Type to a Grouping Value Set
CDA-20703 | 2023-06-22 | X | Update Value Set Intervention Preferences at End of Life Grouping | 6/26/2023 - done and Jira ticket marked change applied. |  | Lisa N/Gay D: 17-0-0 | Updated Value Set Intervention Preferences at End of Life Grouping
CDA-20704 | 2023-06-23 | X | Add additional concepts to Advance Directives Categories Value Set | 6/26/2023 - done and Jira ticket marked change applied. |  | Lisa N/Gay D: 17-0-0
CDA-20708 | 2023-06-23 | X | Create new Value Set Witness Participant Role options | 6/26/2023 - VS Change Completed - OID: 2.16.840.1.113762.1.4.1115.20 Name: PACP Advance Directive Witness types Still need to make the needed template constraint changes to bind this new VS into the template. |  | Lisa N/Gay D: 17-0-0
| CDA-20345 | 2023-07-27 | Block-2023-06-21 | Consider Removing Chapter 4 of Volume 1 | Not Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20376 | 2023-07-27 | Block-2023-06-21 | Update PACP to be consistent with FHIR for Jurisdiction | Consider for Future Use | Lisa N/Anne P: 15-0-0
| CDA-20705 | 2023-06-22 | SDWG Discussion | Add constraint on Witness for participant/participantRole/code | Persuasive | Lisa N/Gay D: 17-0-0
| CDA-20706 | 2023-07-27 | Block-2023-06-21 | Remove Containment constraints for entries with duplicated Section locations to align with FHIR ADI IG | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20707 | 2023-07-27 | Block-2023-06-21 | Rename Entry to Align with FHIR ADI IG From: Advance Directive Change Preference Observation \ | Persuasive | Lisa N/Anne P: 15-0-0
to: Preference to Permit or Deny Future Changes Based on Mental Status
| CDA-20709 | 2023-07-27 | Block-2023-06-21 | Create new entry for GPP for Certain Conditions which links Concern to Goals and Preferences or Priorities | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20710 | 2023-07-27 | Block-2023-06-21 | Remove Care Experience Preferences entry from GPP Upon Death Section | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20715 | 2023-07-27 | Block-2023-07-17 | Remove Personal Health Goal entry from GPP Upon Death Section | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20716 | 2023-07-27 | Block-2023-07-17 | Add an entry template called Personal Advance Directive Document Observation. | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20717 | 2023-07-27 | Block-2023-07-17 | Remove the constraint to permit the use of an Advance Directive Observation entry in the Additional Documentation Section | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20719 | 2023-07-27 | Block-2023-07-17 | Loosen the constraint for the Reference to an external Document from a SHALL to a MAY in the DNR and MOLST Observation templates | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20721 | 2023-07-27 | Block-2023-07-17 | Make a new value set for Condition and Prognosis Scenarios. Add 75777-3 and 75778-1. | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20722 | 2023-07-27 | Block-2023-07-17 | Remove these concepts from the End of Life Preferences Value Set. 75777-3 and 75778-1 | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20723 | 2023-07-27 | Block-2023-07-17 | Add 75793-0 to the Upon Death Preferences Value Set | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20724 | 2023-07-27 | Block-2023-07-17 | For Upon Death Preferences entry template, add a coded precondition that includes the code for 419620001 ¦ Death (event) | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20725 | 2023-07-27 | Block-2023-07-17 | Add 95541-9 to the Care Experience Preferences at EOL Grouping Value Set | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20726 | 2023-07-27 | Block-2023-07-17 | Add 81345-1 to the urn:oid:2.16.840.1.113762.1.4.1115.13 Healthcare Agent Powers or Limitations Indicator value set | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20727 | 2023-07-27 | Block-2023-07-17 | Add guidance that an Advance Directives "advisor" MAY be represented as an informant at the document level. | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20728 | 2023-07-27 | Block-2023-07-17 | Add 81347-7 to the urn:oid:2.16.840.1.113762.1.4.1115.13 Healthcare Agent Powers or Limitations Indicator value set | Persuasive | Lisa N/Anne P: 15-0-0
| CDA-20729 | 2023-08-03 | Block-2023-07-25 | Replace the Assertion Code of Notary Observation with LOINC 81372-5 | Persuasive | Lisa N/Didi D: 20-0-0
| CDA-20731 | 2023-08-03 | Block-2023-07-25 | Replace the Assertion Code of Witness Observation with a value set (Witness Observation) to hold the concepts for First, Second and Third Witnesses. | Persuasive | Lisa N/Didi D: 20-0-0
| CDA-20730 | 2023-08-03 | Block-2023-07-25 | Create a separate template for Author Attestation Observation that is separate from the Witness Observation. | Persuasive | Lisa N/Didi D: 20-0-0
| CDA-20732 | 2023-08-03 | Block-2023-07-25 | Modify the Notary Observation to alter how the State and County of Commission information is recorded. | Persuasive | Lisa N/Didi D: 20-0-0
| CDA-20733 | 2023-08-03 | Block-2023-07-31 | Fix the Personal Priorities Organizer to (MAY) contain Care Experience Preferences and Upon Death Preferences as well. | Persuasive | Lisa N/Didi D: 18-0-0
| CDA-20734 | 2023-08-03 | Block-2023-07-31 | Consider using ClinicalDocument/sdtc:statusCode as a way to mirror the the documentStatus and Composition.status information being specified in the FHIR ADI IG. | Considered for Future Use | Lisa N/Didi D: 18-0-0
| CDA-20738 | 2023-08-17 | Block-2023-08-17 | Change the value set for ClinicalDocument.code to be Personal Advance Directive Document Types (urn:oid:2.16.840.1.113762.1.4.1115.22). | Persuasive | Lisa N/Brett M: 12-0-2
| CDA-20739 | 2023-08-17 | Block-2023-08-17 | Modify the name of templates representing preferences to use Preference rather than Observation: | Persuasive | Lisa N/Brett M: 12-0-2
Upon Death Observation→Upon Dealth Preference
Organ Donation Observation→Organ Donation Preference
Autopsy Observation→Autopsy Preference
| CDA-20741 | 2023-08-31 | Block-2023-08-24 | Change the name of the MOLST Observation template (urn:hl7ii:2.16.840.1.113883.4.823.1.4.8:2023-08-28) to match more generally the term Portable Medical Order. | Persuasive | Lisa N/Brett M: 12-0-0
| pre-applied. |  |  | MOLST Observation→PMO Observation
| CDA-20742 | 2023-08-31 | Block-2023-08-24 | Relax the constraints from SHOULD to MAY for sections that May not be in all types of Personal Advance Directive Documents | Persuasive | Lisa N/Brett M: 12-0-0
| pre-applied. |  |  | 3. The structuredBody, if present, MAY contain zero or one [0..1] component (CONF:5547-33640) such that it
1. SHALL contain exactly one [1..1] GPP Personal Care Experience Section (identifier: urn:hl7ii:2.16.840.1.113883.4.823.1.3.6:2023-08-28) (CONF:5547-33641).
4. The structuredBody, if present, MAY contain zero or one [0..1] component (CONF:5547-33642) such that it
1. SHALL contain exactly one [1..1] GPP for Certain Conditions Section (identifier: urn:hl7ii:2.16.840.1.113883.4.823.1.3.4:2023-08-28) (CONF:5547-33643).
5. The structuredBody, if present, MAY contain zero or one [0..1] component (CONF:5547-33644) such that it
1. SHALL contain exactly one [1..1] GPP Upon Death Section (identifier: urn:hl7ii:2.16.840.1.113883.4.823.1.3.5:2023-08-28) (CONF:5547-33645).
6. The structuredBody, if present, MAY contain zero or one [0..1] component (CONF:5547-33813) such that it
1. SHALL contain exactly one [1..1] Additional Documentation Section (identifier: urn:hl7ii:2.16.840.1.113883.4.823.1.3.8:2023-08-28) (CONF:5547-33814).
| CDA-20742 | 2023-08-31 | Block-2023-08-24 | Tighten the constraint to SHALL for Administrative Information Section so that the document will always include the section that shows if the author has signed it or not. | Persuasive | Lisa N/Brett M: 12-0-0
| pre-applied. |  |  | Change to this:
The structuredBody, if present, SHOULD contain zero or one [0..1] SHALL contain exactly one [1..1] component (CONF:5547-32997) such that it
1) SHALL contain exactly one [1..1] Administrative Information Section (identifier: urn:hl7ii:2.16.840.1.113883.4.823.1.3.7:2023-08-28) (CONF:5547-32998).
| CDA-20744 | 2023-08-31 | Block-2023-08-24 | Update the Upon Death Preference template to use Value Set Upon Death Preferences with OID urn:oid:2.16.840.1.113762.1.4.1115.15. | Persuasive | Lisa N/Brett M: 12-0-0
pre-applied.
The OID urn:oid:2.16.840.1.113762.1.4.1115.16 was not available in VSAC, so we need to reference the Value Set using this other OID.
| CDA-20745 | 2023-08-31 | Block-2023-08-24 | Modify the Personal Advance Directive Document Observation to remove nesting the jurisdiction and Authoritative Form Source | Persuasive | Lisa N/Brett M: 12-0-0
pre-applied.
Remove the nesting of these entryRelationships and make including the jurisdiction and authoritative form source information optional.
| CDA-20746 | 2023-08-31 | Block-2023-08-24 | Modify the DNR Observation Template to follow the pattern for the Personal Advance Directive Document Observation. | Persuasive | Lisa N/Brett M: 12-0-0
pre-applied.
| CDA-20747 | 2023-08-31 | Block-2023-08-24 | Modify the PMO Observation Template to follow the pattern for the Personal Advance Directive Document Observation. | Persuasive | Lisa N/Brett M: 12-0-0
pre-applied.
| CDA-20748 | 2023-08-31 | Block-2023-08-24 | Modify Volume 1 to use updated template identifiers/versions and revise guidance to explain the role for Informant. | Persuasive | Lisa N/Brett M: 12-0-0
pre-applied
| CDA-20749 | 2023-09-11 | Block-2023-09-07 | Update the formatCodes in the PACP Document template. | Persuasive | Lisa N/Brett M: 6-0-0
| CDA-20750 | 2023-09-11 | Block-2023-09-07 | Add a UP Ticket to request creation of new formatCodes | Persuasive | Lisa N/Brett M: 6-0-0
| CDA-20751 | 2023-09-11 | Block-2023-09-07 | Request LOINC to create a new concept for Life Sustaining Treatments which doesn't include "when pregnant". | Not needed - Withdrawn | Lisa N/Brett M: 6-0-0
| CDA-20752 | 2023-09-11 | Block-2023-09-07 | Update Upon Death Preference template constraint to use the 2023-08-28 version. | Persuasive | Lisa N/Brett M: 6-0-0
| CDA-20753 | 2023-09-11 | Block-2023-09-07 | In the Upon Death Preference Template, move the single value binding constraint off the precondition/code element onto the code attribute of the code element. | Persuasive | Lisa N/Brett M: 6-0-0
| CDA-20754 | 2023-09-11 | Block-2023-09-07 | Fix the Intervention Preference Under Health Scenario Template to change the vocabulary binding for the precondition/code element. | Persuasive | Lisa N/Brett M: 6-0-0
Make the vocabulary binding a SHOULD binding on the precondition/code/@code attribute to value set AD Condition and Prognosis Scenarios (2.16.840.1.113762.1.4.1115.23)
| CDA-20755 | 2023-09-11 | Block-2023-09-07 | Version the Authenticated Copy template to create the 2022-03-25 version. | Persuasive | Lisa N/Brett M: 6-0-0
| CDA-20756 | 2023-09-11 | Block-2023-09-07 | Undue changes to allow for the header to use Informant to represent a facilitator helping the person to make their Directives. | Persuasive | Lisa N/Brett M: 6-0-0
Guidance was already present to use ServiceEvent/performer for this role. This change needs to undue prior changes in Volume 1 (CDA-20748) and in Volume 2 to the PACP Header Template.
Address the Template changes - Block Vote Block-2023-09-11 - to be voted on 2023-09-12
| Jira Ticket | Approved on Date | Note or Block Vote # | Short Title | Proposed Resolution | Vote Details
| CDA-20760 |  | Block-2023-09-11 | Add MAY constraint on ClinicalDocument for use of sdtc:statusCode. | Persuasive
| CDA-20761 |  | Block-2023-09-11 | Add SHOULD binding for ClinicalDocument/sdtc:statusCode to FHIR R5 CompositionStatus value set and use a binding stability of STATIC as of 8/28/2023. | Not Persuasive
| CDA-20762 |  | Block-2023-09-11 | Apply a tighter constraints for ClinicalDocument/sdtc:statusCode to ensure that the status of the document is always included and the concepts from CompositionStatus are included as a minimum. Additional concepts for expressing the status of the document from a different codeSystem may be used as long as the concepts can be mapped to CompositionStatus concepts. | Not Persuasive